PROJECT PLANNING PHASE

Streamlining IT Procurement: Automating Standard Laptop Orders with Flow Designer

Prepared using the supplied Planning Logic and Project Planning Template structure.

# 1. Project Planning Template

| Field | Project Details |
| --- | --- |
| Date | 28 September 2026 |
| Team ID | To be assigned |
| Project Name | Streamlining IT Procurement: Automating Standard Laptop Orders with Flow Designer |
| Planning Method | Agile / Scrum |
| Sprint Duration | 6 working days |
| Planned Sprints | 4 |
| Maximum Marks | 5 Marks |

# 2. Project Objective

Automate the standard laptop procurement request process so that eligible employees can submit a standard laptop order, trigger validation and approval steps, create/route the procurement work, and receive status notifications with minimal manual intervention.

# 3. Flow Designer – Proposed Automation Flow

| Flow Step | Logic / Condition | Flow Designer Activity |
| --- | --- | --- |
| 1. Request Submitted | Employee submits a standard laptop request from the approved catalog/request form. | Trigger flow |
| 2. Validate Request | Check requester details, employment/eligibility, required fields, and standard laptop selection. | Validation |
| 3. Check Standard Catalog | Confirm that the requested configuration is within the approved standard laptop model/configuration. | Decision |
| 4. Approval | If approval is required, route the request to the configured approver. | Approval action |
| 5. Create Procurement Task | Create and assign the procurement/purchasing task with the validated laptop details. | Create task |
| 6. Notify Stakeholders | Send request/approval/procurement status notifications to the requester and relevant team. | Notification |
| 7. Fulfillment Update | Update the request as procurement progresses and capture fulfillment/asset details when available. | Record update |
| 8. Close Request | Confirm completion, update final status, and notify the requester. | Closure |

# 4. Planning Logic

The supplied Planning Logic defines a Sprint as a fixed period, an Epic as a large project item broken into smaller stories, a Story as a small task within an Epic, and Story Points as an effort estimate using a Fibonacci-style scale (1, 2, 3, 5).

| Sprint | Epic Focus | Planning Logic | Total Story Points |
| --- | --- | --- | --- |
| Sprint 1 | Request Intake & Standardization | Capture laptop request, standard catalog, requester validation and request data. | 14 |
| Sprint 2 | Validation & Approval | Eligibility checks, standard configuration validation and approval routing. | 14 |
| Sprint 3 | Procurement Automation | Procurement task creation, assignment, status updates and notifications. | 14 |
| Sprint 4 | Fulfillment, Testing & Closure | Fulfillment updates, end-to-end testing, exception handling, reporting and closure. | 14 |

Total Story Points = 14 + 14 + 14 + 14 = 56

Velocity = Total Story Points Completed / Number of Sprints = 56 / 4 = 14 Story Points per Sprint.

Planned average velocity: 14 story points per sprint.

# 5. Product Backlog, Sprint Planning, Stories & Story Points

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Request Intake & Standardization | USN-1 | As an employee, I can submit a standard laptop request with the required details. | 3 | High |
| Sprint-1 | Request Intake & Standardization | USN-2 | As an employee, I can select an approved standard laptop configuration from the catalog. | 3 | High |
| Sprint-1 | Request Intake & Standardization | USN-3 | As an IT user, I can view the submitted request with requester and laptop details. | 3 | Medium |
| Sprint-1 | Request Intake & Standardization | USN-4 | As the system, I can validate mandatory request fields before processing. | 5 | High |
| Sprint-2 | Validation & Approval | USN-5 | As the system, I can validate requester eligibility for a standard laptop order. | 3 | High |
| Sprint-2 | Validation & Approval | USN-6 | As the system, I can confirm that the selected configuration is an approved standard. | 3 | High |
| Sprint-2 | Validation & Approval | USN-7 | As an approver, I can approve or reject a laptop request through the defined approval step. | 5 | High |
| Sprint-2 | Validation & Approval | USN-8 | As the requester, I receive a notification when approval is completed. | 3 | Medium |
| Sprint-3 | Procurement Automation | USN-9 | As the system, I can automatically create a procurement task after successful validation/approval. | 5 | High |
| Sprint-3 | Procurement Automation | USN-10 | As the procurement team, I can receive an assigned task containing the required laptop details. | 3 | High |
| Sprint-3 | Procurement Automation | USN-11 | As the requester, I receive status notifications when procurement processing changes. | 3 | Medium |
| Sprint-3 | Procurement Automation | USN-12 | As an IT user, I can update procurement status without recreating the request. | 3 | Medium |
| Sprint-4 | Fulfillment, Testing & Closure | USN-13 | As the fulfillment team, I can record fulfillment and asset information against the request. | 3 | High |
| Sprint-4 | Fulfillment, Testing & Closure | USN-14 | As the system, I can close the request after successful fulfillment confirmation. | 3 | High |
| Sprint-4 | Fulfillment, Testing & Closure | USN-15 | As an IT user, I can handle an exception when validation, approval or procurement fails. | 5 | High |
| Sprint-4 | Fulfillment, Testing & Closure | USN-16 | As a project team member, I can verify the end-to-end Flow Designer automation using test scenarios. | 3 | High |

# 6. Project Tracker, Velocity & Sprint Schedule

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 14 | 6 Days | To be scheduled | To be scheduled | 14 planned | To be scheduled |
| Sprint-2 | 14 | 6 Days | To be scheduled | To be scheduled | 14 planned | To be scheduled |
| Sprint-3 | 14 | 6 Days | To be scheduled | To be scheduled | 14 planned | To be scheduled |
| Sprint-4 | 14 | 6 Days | To be scheduled | To be scheduled | 14 planned | To be scheduled |

# 7. Sprint Deliverables

| Sprint | Expected Deliverable |
| --- | --- |
| Sprint-1 | Request form/catalog design; mandatory fields; standard laptop configuration; initial request validation. |
| Sprint-2 | Eligibility validation; standard configuration decision; approval flow; approval notifications. |
| Sprint-3 | Automated procurement task; assignment; status updates; requester notifications. |
| Sprint-4 | Fulfillment/asset updates; exception path; end-to-end testing; closure and final documentation. |

# 8. Burndown Chart – Planning Data

The supplied template describes a burndown chart as work remaining versus time. For this project, the initial planned work is 56 story points. The following is a simple sprint-level planning baseline; actual completed points should replace the planned values during execution.

| Checkpoint | Planned Remaining Story Points | Target Remaining Story Points |
| --- | --- | --- |
| Start | 56 | 56 |
| End Sprint-1 | 42 | 42 |
| End Sprint-2 | 28 | 28 |
| End Sprint-3 | 14 | 14 |
| End Sprint-4 | 0 | 0 |

# 9. Definition of Done

User story acceptance criteria are met and tested.

Flow Designer logic executes successfully for the intended standard-laptop scenario.

Required approvals, tasks, status updates and notifications are validated.

Exception handling is tested for validation, approval and procurement failures.

Request and fulfillment information is correctly captured and the request can be closed.

Relevant project documentation and test evidence are completed.

# 10. Assumptions / Items to Confirm

Exact standard laptop models/configurations and eligibility rules are to be provided by the IT procurement team.

The approval hierarchy and approval thresholds are to be confirmed.

Procurement task ownership and fulfillment workflow are to be confirmed.

Actual sprint dates and team-member names are intentionally left open because they were not supplied in the reference templates.

# 11. Reference Basis

This canvas follows the supplied Project Planning Template sections: Product Backlog, Sprint Schedule and Estimation; Project Tracker; Velocity; and Burndown Chart. The story-point approach follows the supplied Planning Logic example using 1, 2, 3 and 5 point estimates.